## Task Management
33 | MOVIE PROJECT
Requirements: https://apicrm.cybersoft.edu.vn/files/02-03-2023-02-16-09-api-movie.pdf ,
Deploy Link: https://bcs-07-capstone-3-g9-movie.vercel.app/
Youtube Demo: https://www.youtube.com/watch?v=fPwA2zaYBPU&ab_channel=NewbieDevHuynh
Team member
1 | Huỳnh Quang Bảo
2 | Nguyễn Đình Anh Hào
3 | Đặng Thùy Linh
Page | Components / Features | API | Start Date | Finish Date | % Completion | Assigned Member | Notes
| Setup and Self-research |  | 19/07/2023 - 21/07/2023 |  |  | All
USER | Đăng ký - Chi Tiết Phim
| LAYOUT - RESGISTER PAGE | NONE | 2023-07-28 | 2023-07-28 | 100% | Nguyễn Đình Anh Hào
| REGISTER NEW USERS | /api/QuanLyNguoiDung/DangKy | 2023-07-29 | 2023-07-29 | 100% | Nguyễn Đình Anh Hào
| RRRESPONSIVE - REGISTER | NONE | 2023-07-28 | 2023-07-28 | 100% | Nguyễn Đình Anh Hào
| MOVIE DETAIL | /api/QuanLyPhim/LayThongTinPhim?MaPhim=${maPhim} /api/QuanLyRap/LayThongTinLichChieuPhim?MaPhim=${maPhim} | 2023-07-30 | 2023-07-30 | 50% | Nguyễn Đình Anh Hào | Have not get the showtime infomation because actually it is out of scope. Setting show time is not installed in the admin side, so I do not have the data to fetch to the UI in the user side
USER | Đặt vé
| BOOKING | NONE | 2023-07-22 | 2023-07-22 | 100% | Đặng Thuỳ Linh
| CHECKOUT | NONE | 2023-07-23 | 2023-07-23 | 100% | Đặng Thuỳ Linh
| REDUCER | NONE | 2023-07-23 | 2023-07-24 | 100% | Đặng Thuỳ Linh
| REDUX | NONE | 2023-07-25 | 2023-07-26 | 100% | Đặng Thuỳ Linh
ADMIN | Quản Lý Phim và Người Dùng
| LOGIN / LOGOUT | /api/QuanLyNguoiDung/DangNhap | 2023-07-26 | 2023-07-26 | 100% | Huỳnh Quang Bảo
| ADMIN TEMPLATE (UI) RESPONSIVE | NONE | 2023-07-27 | 2023-07-27 | 90% | Huỳnh Quang Bảo | Active tab is still not perfect - when clicking the "Add" buttons, the url changes but the active tab in the navbar do not change yet
| USER DRAWER | NONE | 2023-07-27 | 2023-07-27 | 100% | Huỳnh Quang Bảo
| EDIT USER | /api/QuanLyNguoiDung/CapNhatThongTinNguoiDung | 2023-07-29 | 2023-07-30 | 100% | Huỳnh Quang Bảo
| LAYOUT - MOVIE TABS RESPONSIVE | NONE | 2023-07-27 | 2023-07-27 | 100% | Huỳnh Quang Bảo
| VIEW ALL MOVIES | /api/QuanLyPhim/LayDanhSachPhim?maNhom=GP01 | 2023-07-27 | 2023-08-27 | 100% | Huỳnh Quang Bảo
| SEARCH MOVIES | /api/QuanLyPhim/LayDanhSachPhim?maNhom=GP01&tenPhim=${tenPhim} | 2023-07-27 | 2023-07-30 | 100% | Huỳnh Quang Bảo
| ADD NEW MOVIES | /api/QuanLyPhim/ThemPhimUploadHinh | 2023-07-28 | 2023-07-28 | 100% | Huỳnh Quang Bảo
| EDIT MOVIES | /api/QuanLyPhim/CapNhatPhimUpload | 2023-07-28 | 2023-07-29 | 100% | Huỳnh Quang Bảo
| DELETE MOVIES | /api/QuanLyPhim/XoaPhim?MaPhim=${MaPhim} | 2023-07-29 | 2023-07-29 | 100% | Huỳnh Quang Bảo